## Knowlege Transfer Sessi
Support Transition Entry Criteria | Version: 2023.04
Customer Name Enter here -->
Question | Answer
What modules in Saviynt are being used?
What are the endpoints, security systems?
What are the connectors?
What kind of Approvals workflow do you have (add and reject)?
Identity lifecycle flow of a user (Hire, termination, rehire, job change etc)
Are there any data manipulations after user imports and accounts import?
Custom Queries and what are the use cases? Who created them?
Are you planning any customizations or JAR files?
Job schedules and dependencies (What are the job dependencies and why the schedule is the way it is)
Which SSO IDP is being used?
Any specific Analytic Controls (Use case specific) implemented? (apart from generic controls)
How are the use cases related to Termination being handled?
Are the Enterprise/Firefighter roles being used?
Complete Rules Overview (Technical, User update)
Is there any Data manipulation before campaign launch?
Saviynt for Saviynt? (If Yes, then overview on what it is being used for)
Are there any other changes or enhancements that we completed prior to migration?
NOTE: Focus knowledge sharing sessions on unique or customized functions to reduce time commitment

## Implementation transition to Su
Support Transition Entry Criteria | Version: 2023.04
Customer Name Enter here -->
Should be completed by the SI during Design
Type | Checklist | Responsible | Provide Details for Justification | Response | Risk | Rating (Red/Yellow/Green) | Comments | Next Steps
Technical Readiness - Connectivity | Has all connectivity been tested?
Technical Readiness - SSO | Has SSO been validated?
Technical Readiness - User Import | Has the User Import process been tested?
Is the import tested with full Prod volumes and Data?
Technical Readiness - Sav Roles/ Saviynt sitemap | Have all custom SAV roles been tested?
Technical Readiness - Application Imports | Performance testing: Have you tested both incremental and full imports?
Have you tested all queries?
Have you tested all job schedules?
Technical Readiness - Provisioning | Are timeouts configured in connectors?
Instant vs Scheduled provisioning (Configs for task execution hierarchy, connector & feature support)
Technical Readiness -Global Configs | Have all global configs been validated?
Are all custom GSP changes validated?
Are there any custom or special configs to understand?
Is SMTP setup and validated?
Technical Readiness - Job Scheduling | Is Job schedule validated and adjusted if needed?
Technical Readiness - User Update and Technical Rules | Have all users update rules been validated?
Technical Readiness - Certifications | Have Certification campaigns been tested?
Technical Readiness - Transport | Is SFTP confgured and tested?
Technical Readiness - Requests | Have request processing been validated?
Are users trained on the new UI (If converting)?
Technical Readiness - User Registration Forms | Are dynamic attributes validated/Tested?
Technical Readiness - Analytics | Have all analytics been tested?
Have analytics been tested with production data and volume?
Documents required | Requirements and Use case document |  | Provide the document link or location
| Architecture and Design document |  | Provide the document link or location
| Configuration and Customization document |  | Provide the document link or location
| Documentation for Initial Data Load |  | Provide the document link or location
| Documentation for Daily Data Load (Reconciliation) |  | Provide the document link or location
| Run Book with Job schedules and business dependencies with Internal Customer SLA that we agreed to as part of Implementation |  | Provide the document link or location
| Code Installation/Deployment steps and Instructions |  | Provide the document link or location
| Test Plan |  | Provide the document link or location
| Test Scripts/Automation |  | Provide the document link or location
| Baseline performance metrics for User Imports, Account Imports, Provisioning etc. |  | Provide the document link or location
| List of all reports with frequency (along with sample reports) |  | Provide the document link or location
Customer Enablement | Customers are ready for the go-live? |  | Partner and customers
Does customer have an operations team defined and prepped go-live?
Monitoring and Alerting | Is control center configured to manage jobs? |  | Provide the details
Environment Setup | Are all environments set up and available?
Is all DNS setup on all environments?
Is alerting setup on all environments?
Are asset inventory updated with the new environments?
Are SC2 server and client configuration validated?
User Acceptance Validation | Are there any outstanding blocking issues prior to go live? |  | Provide the design and owner
| Is the UAT complete with no outstanding issues? |  | Provide the results
| Have all use cases been tested in real-life scenarios in a non-prod environment? |  | Provide the results
Has the Saviynt operational run book been updated including special branding, customizations or special support processing
| Are there any outstanding tickets? |  | There should be none
| Has the customer reviewed and approved the UAT test cases |  | Please provide the approval
Have custom JAR's been validated through an update?
Go-live Readiness | Have the Go-live dates been identified
Have internal CPAM support configs been validated?
Have monthly update dates been established?
Has a DL been provided for communication of updates?
Have all issues found during the Testing been reviewed by the Support team?
Have all issues found during the Testing been planned to be implemented prior to prod go-live?
| Has the customer approved the implementation for go-live |  | Please provide the approval

## Change Log
Change Log
Date | Responsible | Comments | TAB Effected | VERSION