## Slide 1
CPAM
Project Kick Off

## Slide 2
Agenda
Project Team
Key Action Items (Next Steps)
RACI
Project Overview
Scope, Assumptions, Out of Scope, Risks
Project Activities & Timeline

## Slide 3: Project Overview
Background & Objective
Scope
The objective is to help [CUSTOMER] implement Saviynt CPAM solution in order to build a robust Privileged Access Management (PAM) program and strengthen their overall cybersecurity posture.
~10-week estimated timeline for completion for Phase-1 of the project including post go-live Hypercare
~25-week estimated timeline for completion of Phase-2 of the project including post go-live Hypercare
Based on our understanding of [CUSTOMER] scope, we have summarized project scope as below
Phase 1: Building CPAM environment – Addressing core requirements for Audit
Active Directory Privileged Accounts and service Accounts onboarding: Policy based password rotation, Check-in/check-out, Password policy, Credential checkout, Credential Less ADAM(AD Console) access
AWS: One AWS account onboarding, Machine discovery, Session Recording and playback, Workload access method (Credential, Credential Less, and Just in Time), AWS console, Linux and Windows workload protections
Splunk (Security Information and Event Management – SIEM) integration.
OnPerm Vault Integration
Phase 2: Expansion of CPAM
Automatic password rotation (Windows Services, Schedule Tasks)
Service Account Management (Active Directory Service Account management, Strategy definition to reduce service accounts, Service Account removal from Unix servers.
Two (2) AWS accounts onboarding to cover “console, Linux, Windows and DB” workloads to extend phase-1 solution
Solution design to onboard OnPerm infrastructure (Up to 5 sets of unique combinations of machines) to demonstrate JIT, Credential Less, Credential access to Windows/Linux and DB workloads

## Slide 4: Assumptions
The Saviynt resources will deliver the work through the following mechanisms: Email, Phone calls and Zoom (or similar) meetings.
Out of the box connectors will be utilized for integrating with in-scope applications wherever applicable.
Customer will be responsible for UAT & Systems Integration Testing (SIT). Customer will own the test cases, scripts and identifying individuals for UAT. Saviynt will provide information on functional test use cases. Saviynt can assist customer in UAT test case creation if needed.
Saviynt can provide configuration guides and solution implementation steps. Client needs to create operational documentation based on their requirements. Saviynt can assist but will not own any operational documents.
Customer will provide the necessary network connectivity to Development, UAT, and Production environments, so that Saviynt system can connect to Customer system in each environment for troubleshooting and assistance provided.
Customer will ensure the data validation and integrity check of all data and feeds.
Customer will provide information about different types of attributes that need to be set within each target system while provisioning.
Organizational “rollout” within the Customer organization(s) is the responsibility of Customer.
Customer shall communicate to Saviynt any changes in schedule and availability of project personnel, computing hardware, software, resources, or facilities related to the project at least five (5) business days prior to the change.
Customer shall resolve all other environmental issues (including but not limited to application server, databases, and network routing)
Organization change management & communication will be responsibility of Customer.
Prerequisite: Connectivity from Saviynt Security Manager (SSM) to Active Directory, AWS and target workloads/environments in scope.

## Slide 5: Out of Scope
Provisioning, Deprovisioning and JML (Joiner, Mover and Leaver) process for in-scope applications and already onboarding applications.
Active Directory (“AD”) groups creation/management.
Segregation of Duty (“SOD’), Role engineering and mining.
Access Request System configuration for in-scope applications.
Custom development for Access Request System (ARS) forms and other items.
Perform organizational change management.
Configure on-demand reports and/or controls post go-live.
Configure on-going certifications campaigns or any other operational work.
Retirement of any existing platforms or products.
Operational support activities.
Development of custom connectors.
Data clean-up, including resolution of incorrect or missing identity correlation data.
Development or execution of a communication plan.
Development or execution of test scripts.
Project management and/or coordination of activities between Customer and third-party stakeholders.
Product Training and enablement of end Users.

## Slide 6: Risks and Mitigation
Risk | Mitigation Plan
Delays in resource Onboarding | Work with [CUSTOMER] to expedite onboarding and Identify the impact of delay and possible workarounds.
SME/POC availability | [CUSTOMER] : Customer point of contacts & Stakeholders are identified and available before the start of the project. [PARTNER]
Delays on requirements Sign-off | Critical item. Request customer to signoff to be provided within 5 days.

## Slide 7: Project Activities & Timeline – Phase-1
*Timeline is calculated based on our estimates from other engagements and subject to change depending on project constraints
Requirements and Design
W1
W2
W10
W6
W5
W4
W3
W9
W8
W7
Project Start Date
Integrated [CUSTOMER] Vault – Dev * Date
CPAM Go-Live date
UAT Start Date
Implementation
UAT and Go Live
Hyper Care
Upgrade Hyper Care Complete - Prod
Date *
CPAM Hyper Care
Complete Date

## Slide 8: [PARTNER] Team
Role | Name | Title | Responsibility
Account Level Management |  |  | 
Project Team |  |  | 

## Slide 9: [CUSTOMER] CPAM Project Team
Role | Name | Title
Executive Sponsor |  | 
Project Leader |  | 
Solution Architect |  | 
PMO |  | 
Manager IAM |  | 
SME1 |  | 

## Slide 10: Saviynt RACI – Phase 1
Stage | Saviynt CPAM Cloud Managed Platform RACI | [PARTNER] | [CUSTOMER]
Implementation | Build |  | 
 | Saviynt Application Setup in Environment | R, A, C | I,A
 | Requirement Definition | C, I | R,A
 | Architecture and Design | R,A | C,I,A
 | Saviynt Configuration (Connectors, Workflows, tasks, jobs, Bootstrapping, policies, etc.) | R,A | C,I,A
 | Data Setup in Saviynt (Users, Accounts, Policies, UserGroups, Roles, etc.) | A | R
 | UI Changes | R | I
 | Connections to Upstream/downstream applications | R | C,I,A
 | Application and workloads on-boarding | R | A,C,I
 | Project Management | C | R, A
 | Quality Assurance | R | R
 | Environment Configurations (Platform) | R | I
 | Performance Optimization and Tuning | R | I
 | Roll Out |  | 
 | Migration of configuration across environments (Dev-to-prod) | R | C,I
 | Data Migration/Bootstrap/PAM-Policies | R | A
R – Responsible | A - Accountable | C - Consulted | I - Informed

## Slide 11: Key Action Items (Next Steps)
SOW sign-off
Identify and share key point of contacts (POCs) to facilitate discovery and implementation
Prepare requirement gathering artifacts, templates for solution design
01
02
03
04
Schedule project update cadence meetings
Plan and schedule all discovery sessions between [CUSTOMER] and [PARTNER]

## Slide 12
Learn more
To learn more about Saviynt Solutions Exchange, visit our website https://saviynt.com/exchange/solutions
Questions? Contact our team.
Partner Solution Lead:
Mudit Kumar Sharma, Sr. Manager - Partner Solutions mudit.sharma@saviynt.com
Mudit Sharma
Partner Solutions
Suraj Krishnaiah
VP - Saviynt University

## Slide 13
Thank you