## Sheet1
Task Mode | Task Name | Duration | Start | Finish | Predecessors | Resource Names | Requirement Mapping/comments | % Work Complete
Manually Scheduled | Customer CPAM implementation | [6 empty] | 0%
Manually Scheduled | Project pre start activities | 15 days | [5 empty] | 0%
Auto Scheduled | Onboard PAM resources | 15 days | [5 empty] | 0%
Auto Scheduled | Infrastructure | 1 day | [5 empty] | 0%
Auto Scheduled | Network connectivity validation | 1 day | [5 empty] | 0%
Auto Scheduled | Access requirements | 1 day | [5 empty] | 0%
Auto Scheduled | Environment Validation | 1 day | [5 empty] | 0%
Auto Scheduled | product | 5 days | [5 empty] | 0%
Auto Scheduled | Key requirements | 1 day | [5 empty] | 0%
Auto Scheduled | Target Applications | 5 days | [5 empty] | 0%
Auto Scheduled | Upgrade and CPAM enablement | 13 days | [5 empty] | 0%
Auto Scheduled | V2021 Upgrade and migration | 13 days | [5 empty] | 0%
Auto Scheduled | Customer'sIGA migration to V2021 (0.4) with clone DB | 5 days | [5 empty] | 0%
Auto Scheduled | Data migration | 5 days | [5 empty] | 0%
Auto Scheduled | Testing of new Customer'sV2021 0.4 DEV | 5 days | [5 empty] | 0%
Auto Scheduled | Customer'sProd IGA migration to V2021 (0.4) with clone Prod DB | 5 days | [5 empty] | 0%
Auto Scheduled | key Milestone - Environment readiness | 5 days | [5 empty] | 0%
Auto Scheduled | Monthly update on new DEV and Prod environments | 5 days | [5 empty] | 0%
Auto Scheduled | Dev Upgrade to v2021.0.4 | 8 days | [5 empty] | 0%
Auto Scheduled | Dev environment upgrade | 3 days | [5 empty] | 0%
Auto Scheduled | Data Migration for new DEV (v2021.0.4) environment | 3 days |  |  | 18,20 |  |  | 0%
Auto Scheduled | Key - Milestone - Environment rediness for CPAM integration in DEV | 5 days |  |  | 19 |  |  | 0%
Auto Scheduled | Test Prod Upgrade to v2021.0.4 | 5 days | [5 empty] | 0%
Auto Scheduled | Test Prod upgrade - Clone Prod (v2021.0.4) | 10 days | [5 empty] | 0%
Auto Scheduled | Buffer - Time to wait before Prod, clone prod validation | 5 days | [5 empty] | 0%
Auto Scheduled | Cloned Prod signed off by , downtime for PROD confirmed by Customer | 5 days |  |  | 25 |  |  | 0%
Auto Scheduled | Upgrade Hyper care | 0 days |  |  | 26 |  |  | 0%
Manually Scheduled | Phase 1: Building CPAM environment | [6 empty] | 0%
Auto Scheduled | Kickoff – CPAM implementation plan and scope | 1 day | [5 empty] | 0%
Manually Scheduled | Baseline PAM requirements, CPAM workshop and plan adjustment | 1 day | [5 empty] | 0%
Auto Scheduled | Requirement discussion, scope identification and usecases | 4 days | [5 empty] | 0%
Auto Scheduled | Discovery - Target Environments and Cloud accounts | 4 days | [5 empty] | 0%
Auto Scheduled | Service Accounts and A Accounts | 4 days |  |  | 30 |  |  | 0%
Auto Scheduled | AWS | 4 days |  |  | 30 |  |  | 0%
Auto Scheduled | Password Policy and Password Procedures | 4 days | [5 empty] | 0%
Auto Scheduled | Length of passwords | 4 days |  |  | 30 |  |  | 0%
Auto Scheduled | Expiration - How often to rotate | 4 days |  |  | 30 |  |  | 0%
Auto Scheduled | Vault Password aging | 4 days |  |  | 30 |  |  | 0%
Auto Scheduled | Policy formulation for Windows, Unix | 4 days |  |  | 30 |  |  | 0%
Auto Scheduled | Policy for other kind of systems/accounts | 4 days |  |  | 30 |  |  | 0%
Auto Scheduled | Hashicorp Vault | 4 days | [5 empty] | 0%
Auto Scheduled | Integration capabilities | 4 days |  |  | 30 |  |  | 0%
Auto Scheduled | Requirements | 4 days |  |  | 30 |  |  | 0%
Auto Scheduled | Logging and SIEM | 4 days | [5 empty] | 0%
Auto Scheduled | Saviynt logs into SIEM - PAM | 4 days |  |  | 30 |  |  | 0%
Auto Scheduled | Approvals and Notifications | 4 days | [5 empty] | 0%
Auto Scheduled | Access Approval or Check-in/Check-out Process | 4 days |  |  | 30 |  |  | 0%
Auto Scheduled | Escalated approval | 4 days |  |  | 30 |  |  | 0%
Auto Scheduled | Email templates and communication | 4 days |  |  | 30 |  |  | 0%
Auto Scheduled | JIT Approval Method | 4 days |  |  | 30 |  |  | 0%
Auto Scheduled | Windows | 4 days | [5 empty] | 0%
Auto Scheduled | Current Process | 4 days |  |  | 30 |  |  | 0%
Auto Scheduled | Account classifications(Credential, CredentialLess, JIT) | 4 days |  |  | 30 |  |  | 0%
Auto Scheduled | Session recording, Password policy and other CPAM processes | 4 days |  |  | 30 |  |  | 0%
Auto Scheduled | Connecting Accounts and configuration | 4 days |  |  | 30 |  |  | 0%
Auto Scheduled | DB | 4 days | [5 empty] | 0%
Auto Scheduled | Current Process | 4 days |  |  | 30 |  |  | 0%
Auto Scheduled | DB Types and connecting methods | 4 days |  |  | 30 |  |  | 0%
Auto Scheduled | Account classifications(Credential, CredentialLess, JIT) | 4 days |  |  | 30 |  |  | 0%
Auto Scheduled | Session recording, Password policy and other CPAM processes | 4 days |  |  | 30 |  |  | 0%
Auto Scheduled | Connecting Accounts and configuration | 4 days |  |  | 30 |  |  | 0%
Auto Scheduled | Console | 4 days | [5 empty] | 0%
Auto Scheduled | Current Process and requirements | 4 days |  |  | 30 |  |  | 0%
Auto Scheduled | Session recording, Password policy and other CPAM processes | 4 days |  |  | 30 |  |  | 0%
Auto Scheduled | Unix | 4 days | [5 empty] | 0%
Auto Scheduled | Current Process | 4 days |  |  | 30 |  |  | 0%
Auto Scheduled | Identification of Configuration Sets (Type of Unix servers in terms of configuration) | 4 days |  |  | 30 |  |  | 0%
Auto Scheduled | SSh Keys | 4 days |  |  | 30 |  |  | 0%
Auto Scheduled | Session recording, Password policy and other CPAM processes | 4 days |  |  | 30 |  |  | 0%
Auto Scheduled | Account classifications(Credential, CredentialLess, JIT) | 4 days |  |  | 30 |  |  | 0%
Auto Scheduled | Command Classification (Restricted, risks) | 4 days |  |  | 30 |  |  | 0%
Auto Scheduled | Connecting Accounts and configuration | 4 days |  |  | 30 |  |  | 0%
Auto Scheduled | Requirements | 7 days | [5 empty] | 0%
Auto Scheduled | Documentation of all requirements | 1 day |  |  | 33,34,36,37,38,39,40,42,43,45,47,48,50,52,53,54,55,57,58,59,60,61,63,64,66,67,68,69,70,71,72 |  |  | 0%
Auto Scheduled | Technical Requirements to CPAM design mapping | 1 day |  |  | 74 |  |  | 0%
Auto Scheduled | Solution Design | 2 days | [5 empty] | 0%
Auto Scheduled | Develop technical architecture diagram inline with OOTB feature (protocol and ports) | 1 day |  |  | 75 |  |  | 0%
Auto Scheduled | Mapped authoritative source schema with Saviynt user schema | 1 day |  |  | 75 |  |  | 0%
Auto Scheduled | Integration architecture of Cloud environments | 1 day |  |  | 75 |  |  | 0%
Auto Scheduled | In scope Endpoints (Linux, Windows and Db) and workflow | 1 day |  |  | 75 |  |  | 0%
Auto Scheduled | Discovery and Bootstrapping | 1 day |  |  | 75 |  |  | 0%
Auto Scheduled | Session Recording retention | 1 day |  |  | 75 |  |  | 0%
Auto Scheduled | PAM policies (Request workflow, keys, Password, Password rotation, Session recording, Check-in/check-out, time to work, etc.) | 1 day |  |  | 75 |  |  | 0%
Auto Scheduled | SIEM Integration and other polices | 1 day |  |  | 75 |  |  | 0%
Auto Scheduled | Password and Password Less Autentication requirements and workflow demonstration | 1 day |  |  | 75 |  |  | 0%
Auto Scheduled | Automatic onboarding of endpoints and accounts. | 1 day |  |  | 75 |  |  | 0%
Auto Scheduled | Solution | 1 day |  |  | 77,78,79,80,81,82,83,84,85,86 |  |  | 0%
Auto Scheduled | Design Discussion | 1 day |  |  | 87 |  |  | 0%
Auto Scheduled | Prioritization of requirements | 1 day |  |  | 88 |  |  | 0%
Auto Scheduled | Success Criteria | 1 day |  |  | 88 |  |  | 0%
Auto Scheduled | Authoritative source user (schema) with Status, Unique attribute and other mandatory attributes | 1 day |  |  | 75,90 |  |  | 0%
Auto Scheduled | Target cloud environment names / attribute mapping | 1 day |  |  | 75,90 |  |  | 0%
Auto Scheduled | List of privilidged accounts for Bootstrapping (Linux, Windows and Db) | 1 day |  |  | 90,75 |  |  | 0%
Auto Scheduled | Process documentation for Production rollout and change communiction | 1 day |  |  | 90 |  |  | 0%
Auto Scheduled | Requirement Validation and Sign-Off by Customer | 1 day |  |  | 89 |  |  | 0%
Auto Scheduled | Implementation | 14 days |  |  | 73FS-1 day |  |  | 0%
Auto Scheduled | Authoritative data source Integration - Workday | 2 days | [5 empty] | 0%
Auto Scheduled | Checking of Identity Attribute Definition and Configuration to map the Identity data between HR System and Saviynt | 2 days |  |  | 88 |  |  | 0%
Auto Scheduled | Assign additional Saviynt end-user SAV Roles during reconciliation for CPAM | 2 days |  |  | 88 |  |  | 0%
Auto Scheduled | Validate identity data load in DEV instance | 2 days |  |  | 88 |  |  | 0%
Auto Scheduled | Creating jobs to import users to Saviynt DEV | 2 days |  |  | 88 |  |  | 0%
Auto Scheduled | Define Identity policy in Saviynt to cover additional agreed usecases | 2 days |  |  | 88 |  |  | 0%
Auto Scheduled | Milestone - Confirm HR integration | 0 days |  |  | 98,99,100,102 |  |  | 0%
Auto Scheduled | Saviynt Vault Integration | 2 days | [5 empty] | 0%
Auto Scheduled | Saviynt Vault connection setup | 2 days | [5 empty] | 0%
Auto Scheduled | Testing Saviynt Vault connections | 2 days |  |  | 88 |  |  | 0%
Auto Scheduled | Storing connection secret | 2 days |  |  | 88 |  |  | 0%
Auto Scheduled | Checking the shared secret on the vault side | 2 days |  |  | 88 |  |  | 0%
Auto Scheduled | Validating HashiCorp after bootstrapping for first account | 2 days |  |  | 88 |  |  | 0%
Auto Scheduled | Checking with HashiCorp team on the vault side | 2 days |  |  | 88 |  |  | 0%
Auto Scheduled | Active Directory | 8 days |  |  | 88 |  |  | 0%
Auto Scheduled | Integration of Active Directory Service Accounts | 2 days |  |  | 88 |  |  | 0%
Auto Scheduled | AD PAM Connector template Setup | 2 days |  |  | 112 |  |  | 0%
Auto Scheduled | Obtain connection details and OOTB connector pre-requisite | 2 days | [5 empty] | 0%
Auto Scheduled | Develop integration design (data mapping) for target system | 2 days |  |  | 103113 |  |  | 0%
Auto Scheduled | Create Security system, endpoints | 2 days |  |  | 103113 |  |  | 0%
Auto Scheduled | PAM config for Active Directory | 2 days |  |  | 103113 |  |  | 0%
Auto Scheduled | Test of the Integration | 2 days |  |  | 103113 |  |  | 0%
Auto Scheduled | PAM policy implementation specific to Active Directory | 2 days |  |  | 118 |  |  | 0%
Auto Scheduled | Milestone - Active Directory Integration Confirmation | 0 days |  |  | 119 |  |  | 0%
Auto Scheduled | Account bootstrapping - AD | 4 days |  |  | 111 |  |  | 0%
Auto Scheduled | PAM.config and other configuration steps | 4 days | [5 empty] | 0%
Auto Scheduled | Sample account bootstrapping | 4 days | [5 empty] | 0%
Auto Scheduled | Account access query | 4 days | [5 empty] | 0%
Auto Scheduled | Validation of access query | 4 days | [5 empty] | 0%
Auto Scheduled | Enable RDP gateway using AD accounts | 4 days | [5 empty] | 0%
Auto Scheduled | Configuration of RDP sessions | 4 days | [5 empty] | 0%
Auto Scheduled | Configuration of Webapps/ADSI using credential-less accounts | 4 days | [5 empty] | 0%
Auto Scheduled | RDP sessions using crednetial-less AD accounts | 4 days | [5 empty] | 0%
Auto Scheduled | RDP sessions using credential AD accounts | 4 days | [5 empty] | 0%
Auto Scheduled | Milestone - Bootstrapping Confirmation for AD | 0 days | [5 empty] | 0%
Auto Scheduled | Policy Configuration - AD | 2 days |  |  | 130 |  |  | 0%
Auto Scheduled | Session Recording | 2 days |  |  | 130 |  |  | 0%
Auto Scheduled | Password requirements | 2 days |  |  | 130 |  |  | 0%
Auto Scheduled | Workflows | 2 days |  |  | 130 |  |  | 0%
Auto Scheduled | other policy configuration | 2 days |  |  | 130 |  |  | 0%
Auto Scheduled | Milestone - Policy configuration AD | 0 days |  |  | 133134135136 |  |  | 0%
Auto Scheduled | SSM Configuration and alignments (functional testing) - AD | 3 days | [5 empty] | 0%
Auto Scheduled | Configure Request forms in Saviynt for each of the in-scope cloud application and endpoint | 3 days | [5 empty] | 0%
Auto Scheduled | Update Application and Entitlement metadata to enable enriched catalogue (If agreed) | 3 days | [5 empty] | 0%
Auto Scheduled | Configure Approval and other notification emails as per requirements | 3 days | [5 empty] | 0%
Auto Scheduled | Validate end to end access request and access process | 3 days | [5 empty] | 0%
Auto Scheduled | Functional testing | 3 days | [5 empty] | 0%
Auto Scheduled | Milestone - AD Ready for UAT | 0 days | [5 empty] | 0%
Auto Scheduled | Knowledge Transition and documentation | 1 day |  |  | 96 |  |  | 0%
Auto Scheduled | Develop a Run book for the in scope functionality | 1 day | [5 empty] | 0%
Auto Scheduled | Conduct KT session to transition the System configuration | 1 day | [5 empty] | 0%
Auto Scheduled | AD, Saviynt Vault, SIEM UAT Support | 4 days |  |  | 96 |  |  | 0%
Auto Scheduled | UAT test cases prepared for the in-scope deliverables | 3 days | [5 empty] | 0%
Auto Scheduled | Prepare UAT test cases and review them with project team | 3 days | [5 empty] | 0%
Auto Scheduled | Provide technical oversight support to the customer during user acceptance testing (UAT) | 3 days | [5 empty] | 0%
Auto Scheduled | Execute UAT cycle as per the scripts | 3 days | [5 empty] | 0%
Auto Scheduled | Milestone - Ready for Production | 1 day |  |  | 152151150149 |  |  | 0%
Auto Scheduled | Production Rollout | 5 days |  |  | 148 |  |  | 0%
Auto Scheduled | Availability of Information to configure connectors, master connection and support bootstrapping in Production | 5 days | [5 empty] | 0%
Auto Scheduled | Prepare the production go-live check list | 5 days | [5 empty] | 0%
Auto Scheduled | End user communication and change management on the customer side | 5 days | [5 empty] | 0%
Auto Scheduled | Production Environment Bootstrapping (Account and Access import) | 5 days | [5 empty] | 0%
Auto Scheduled | Execute production migration as per the plan, PAM enablement | 5 days | [5 empty] | 0%
Auto Scheduled | Perform production validation as per the checklist (weekend activity) | 5 days | [5 empty] | 0%
Auto Scheduled | Hypercare Support (7 calendar days) | 5 days |  |  | 154 |  |  | 0%
Auto Scheduled | Respond to the Saviynt product specific issues during the Hyper care period | 5 days | [5 empty] | 0%
Auto Scheduled | Test of the Integration | 5 days |  |  | 171 |  | Unblocked 6/28 for Linux; windows, DB pending on Remote Powershell | 50%
Auto Scheduled | Milestone - AWS Integration Confirmation | 0 days |  |  | 172171 |  | Unblocked 6/28 for Linux; windows, DB pending on Remote Powershell | 50%