## Project Plan
Task Mode | Task Name | Duration | Start | Finish | Predecessors | Resource Names | Comments | % Complete
Auto Scheduled | IGA
Auto Scheduled | IGA Kick off & Environment Setup
Manually Scheduled | Setup project kick off
Manually Scheduled | Baseline Project Plan |  |  |  | 3SS
Auto Scheduled | Saviynt specific configuration
Manually Scheduled | Setup network connectivity between Saviynt Cloud and Customer DC (Network Pairing)
Manually Scheduled | Finalize on the URL name which will be used across the board
Manually Scheduled | Enable access for the customer and partners involved in the program
Auto Scheduled | Configure customer specific branding
Auto Scheduled | Configure Email service for the customer
Auto Scheduled | SSO Application Onboarding |  |  |  | 5SS
Manually Scheduled | Configure integration with client’s Single Sign-On (SSO) product and Saviynt over Security Assertion Markup Language (SAML) - Azure SSO
Manually Scheduled | W1 Start
Auto Scheduled | Requirements and Design |  |  |  | 13
Manually Scheduled | Develop high-level design document
Auto Scheduled | Complete mapping of attributes
Manually Scheduled | Prepare, review and obtain signoff on Requirements Document with client
Auto Scheduled | Review Design Document |  |  |  | 15
Auto Scheduled | Sign off on Design from customer |  |  |  | 18
Auto Scheduled | Build
Manually Scheduled | Global Configuration
Auto Scheduled | Setup all Global Configuration (Campaign, Identity, Preferences, Request, Task )
Manually Scheduled | Authoritative Data source integration (Saviynt)
Auto Scheduled | Create employee onboarding form
Auto Scheduled | Create contractor onboarding form
Auto Scheduled | Configure rule in Saviynt to generate username
Auto Scheduled | Define rules to generate unique email address
Auto Scheduled | Define birthright provisioning rules to grant Business Roles and application access based on attributes on the onboarding form
Auto Scheduled | Integration with target Applications
Manually Scheduled | Active Directory
Manually Scheduled | Azure Active Directory
Manually Scheduled | FreshService (API based)
Manually Scheduled | Salesforce (OOTB Connector)
Auto Scheduled | DuckCreek
Auto Scheduled | Configure Access Request Process |  |  |  | 29
Auto Scheduled | User Manager Campaigns |  |  |  | 29
Auto Scheduled | IGA UAT Support |  |  |  | 20FS-1 wk
Auto Scheduled | Preparation of UAT test cases for the in-scope deliverables
Auto Scheduled | Review UAT Test cases them with project team |  |  |  | 95
Auto Scheduled | Provide technical oversight support to the customer during user acceptance testing (UAT) |  |  |  | 96
Auto Scheduled | Execute UAT cycle as per the scripts |  |  |  | 96
Auto Scheduled | IGA Knowledge Transition and documentation
Auto Scheduled | KT and Runbook
Auto Scheduled | Develop a Run book for the in scope functionality |  |  |  | 94FF
Auto Scheduled | Conduct KT session to transition the System configuration |  |  |  | 94FF
Auto Scheduled | IGA Production Rollout |  |  |  | 94
Auto Scheduled | IGA Hypercare Support (7 calendar days) |  |  |  | 103
Auto Scheduled | Respond to the Saviynt product specific issues during the Hyper care period
Manually Scheduled
Manually Scheduled
Manually Scheduled | Customer CPAM
Auto Scheduled | Kickoff – CPAM implementation plan and scope
Auto Scheduled | Infrastructure, Environment setup
Auto Scheduled | Requirements and Solution Design |  |  |  | 119
Auto Scheduled | Build |  |  |  | 130
Auto Scheduled | Authoritative data source validation
Auto Scheduled | Checking of Identity Attribute Definition and Configuration to map the Identity data between HR System and Saviynt |  |  |  | 181
Auto Scheduled | Assign additional Saviynt end-user SAV Roles during reconciliation for CPAM |  |  |  | 181
Auto Scheduled | Validate identity data load in DEV instance |  |  |  | 181
Auto Scheduled | Define Identity policy in Saviynt to cover additional agreed usecases |  |  |  | 181
Auto Scheduled | MileStone - Confirm HR integration |  |  |  | 191192193194
Auto Scheduled | AWS |  |  |  | 190
Auto Scheduled | Integration of AWS (Two accounts)
Auto Scheduled | Availability of information to setup AWS connection
Auto Scheduled | AWS Account Integration Setup
Auto Scheduled | Obtain connection details and OOTB connector pre-requisite
Auto Scheduled | Develop integration design (data mapping) for target system
Auto Scheduled | Integration Setup (Specific to cloud environment)
Auto Scheduled | Create Security system, endpoints
Auto Scheduled | Service Account for Linux (PAM config)
Auto Scheduled | Service Account for Windows (PAM config)
Auto Scheduled | Create PAM Config
Auto Scheduled | Test of the Integration |  |  |  | 206
Auto Scheduled | Milestone - AWS Integration Confirmation |  |  |  | 206207
Auto Scheduled | Machine and account bootstrapping - AWS |  |  |  | 197
Auto Scheduled | Endpoint discovery
Auto Scheduled | Account discovey
Auto Scheduled | Integration test for Linux
Auto Scheduled | Integration test for Windows
Auto Scheduled | Account level policy alignment
Auto Scheduled | Milestone - Bootstrapping Confirmation |  |  |  | 213214
Auto Scheduled | Policy Configuration - AWS |  |  |  | 209
Auto Scheduled | Time to work
Auto Scheduled | Session Recording
Auto Scheduled | Password requirements
Auto Scheduled | Workflows
Auto Scheduled | other policy configuration
Auto Scheduled | Milestone - Policy configuration complete for AWS |  |  |  | 217218219220221
Auto Scheduled | SSM Configuration and alignments (functional testing) - AWS |  |  |  | 216
Auto Scheduled | Configure Request forms in Saviynt for each of the in-scope cloud application and endpoint
Auto Scheduled | Update Application and Entitlement metadata to enable enriched catalogue (If agreed)
Auto Scheduled | Configure Approval and other notification emails as per requirements
Auto Scheduled | Validate end to end access request and access process
Auto Scheduled | Functional testing
Auto Scheduled | Milestone - AWS Ready for UAT |  |  |  | 224225226227228
Auto Scheduled | Buffer for AWS integration |  |  |  | 223
Auto Scheduled | SIEM integration
Auto Scheduled | Generate analytics record/report for CPAM logs
Auto Scheduled | Assign appropriate API access to an API user
Auto Scheduled | Test the API for CPAM data
Auto Scheduled | Provide API details to Customer Q-Radar team to consume
Auto Scheduled | Confgure and Share default reports
Auto Scheduled | SIEM configuration to read Saviynt API
Auto Scheduled | SIEM Functionality Demo to Customer |  |  |  | 2.3223e+17
Auto Scheduled | CPAM UAT Support |  |  |  | 189
Auto Scheduled | UAT test cases prepared for the in-scope deliverables
Auto Scheduled | Prepare UAT test cases and review them with project team
Auto Scheduled | Provide technical oversight support to the customer during user acceptance testing (UAT)
Auto Scheduled | Execute UAT cycle as per the scripts
Auto Scheduled | Milestone - Ready for Production |  |  |  | 240241242243
Auto Scheduled | CPAM Knowledge Transition and documentation |  |  |  | 189
Auto Scheduled | Develop a Run book for the in scope functionality |  |  |  | 229
Auto Scheduled | Conduct KT session to transition the System configuration |  |  |  | 229
Auto Scheduled | CPAM Production Rollout |  |  |  | 239
Auto Scheduled | Availability of Information to configure connectors, master connection and support bootstrapping in Production
Auto Scheduled | Prepare the production go-live check list |  |  |  | 239
Auto Scheduled | Create a change ticket on Saviynt side and attach all the design and deployment artifacts |  |  |  | 239
Auto Scheduled | End user communication and change management on the customer side |  |  |  | 239
Auto Scheduled | Production Environment Bootstrapping (Account and Access import) |  |  |  | 252
Auto Scheduled | Execute production migration as per the plan, PAM enablement |  |  |  | 253
Auto Scheduled | Perform production validation as per the checklist (weekend activity) |  |  |  | 254
Auto Scheduled | CPAM Hypercare Support (14 calendar days) |  |  |  | 248
Auto Scheduled | Respond to the Saviynt product specific issues during the Hyper care period